## Sheet1
Project stage | content | start | end
Record and convert the lectures notes for the Neurohacking in R 2.0 (JM is instructor) being filmed | Record Lecture | May-01-2018 | Jul-01-2018
Call to instructors who are creating MOOCs or have created MOOCs. The goal is to get materials converted to an automated course. | Call for MOOCs | May-01-2018 | June-01-2018
Develop scripts how to automatically how to read in PowerPoint slides and notes into R to convert them into slides and script combinations (using the officer package) and the documentation | PowerPoint Notes Pipeline | May-01-2018 | Jul-01-2018
Semiannual Assessment of Project | Assessment | Nov-01-2018 | NA
Workflow documentation for using RMarkdown slides | Document Rmarkdown | May-01-2018 | Aug-01-2018
Workflow documentation for using Google slides and scripts | Document Google Slides | May-01-2018 | Aug-01-2018
Workflow documentation for general images and scripts | Document General Workflow | May-01-2018 | Aug-01-2018
Create R Shiny application. Do multiple 1 hour tutorials on how to use the platform | Shiny Application | Aug-01-2018 | Oct-01-2018
Have instructors convert materials on R shiny platform | Instructors use Shiny conversion | Oct-01-2018 | Dec-01-2018
DELTA Showcase | DELTA Showcase | Mar-01-2019 | NA
Perform poll on student assessment and compile results | Poll Students | Dec-01-2018 | Sep-01-2019
Perform analysis on student performance from Coursera data | Analyze Coursera Data | Mar-01-2019 | Sep-01-2019
Project Completion | Completion | Sep-01-2019 | NA